## Sheet1
| Planned Value ($23,000) | Earned Value ($20,000) | Actual Cost ($25,000) | Budget at Completion ($120,00)
Questions
Cost Variance | -5000 | [5 empty] | B.) How is the project doing? Is it ahead of schedule or behind schedule? Is it under budget or over budget? | The project is doing poorly. The work is over budget as is also behind schedule.
Schedule Variance | -3000 | [5 empty] | C.) Is the project performing better or worse than planned? | EAC = $150.000. The project is performing worse that planned.
Cost Performance Index | 0.8 | [5 empty] | D.) Estimated time to complete | 13.79 months
Schedule Performance Index | 0.86957
Schedule Performance Index | 0.86957
|  | actual cost | earned value | planned value | bac | eac
| 1 | 2083 | 1666 | 1916
| 2 | 4166 | 3332 | 3832
| 3 | 6249 | 4998.66 | 5748
| 4 | 8332 | 6664 | 7664
| 5 | 10370 | 8330 | 9580
| 6 | 12453 | 9996 | 11246
| 7 | 14536 | 11662 | 13162
| 8 | 16619 | 13328 | 15078
| 9 | 18702 | 14994 | 16994
| 10 | 20785 | 16660 | 18910
| 11 | 22868 | 18326 | 20826
| 12 | 25000 | 20000 | 23000 | 120000
13
| 14 |  |  |  |  | 150000